## RMMM
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contingency Plan | Responsible | Status | Last modified | Probability Score |  | Impact Score
1 | Team | Inexperience team member | 5 | 4 | 20 | Pro-actively involve team members | Uneven workload | n/a | All |  | 2025-04-12 | Very low: 1 | < 1% | < 1% / 1 day
2 | Team | Personnel shortfalls | 1 | 1 | 1 | Provide support | Repeated absence in lectures | n/a | n/a | n/a | 2025-04-12 | Low: 2 | <10% | < 5% / 1 week
3 | User | Lack of co-operation from users | 1 | 1 | 1 | Open communication | n/a | Proactive asking for feedback | n/a | n/a | 2025-04-12 | Medium: 3 | < 20% | < 10% / 2 weeks
4 | Require-ments | Incorrect system requirements | 2 | 3 | 6 | n/a | n/a | n/a | n/a | n/a | 2025-04-12 | High: 4 | < 50% | < 20% / 1 month
5 | Require-ments | Misunderstanding of requirements | 2 | 2 | 4 | Check requirements regularly | Client is unhappy | Re-assess requirements | Christoph | ? | 2025-04-12 | Very high: 5 | ≥ 50% | ≥ 20% / 1 month
6 | Planning & Control | Lack of effective project management technology | 3 | 3 | 9 | Learn the tool | Tooling issues | Switch tooling | Hagen |  | 2025-04-12
7 | Planning & Control | Poor project planning | 4 | 4 | 16 | Stick to weekly scrum sprints | ? | ? | All |  | 2025-04-12
8 | Project Comple-xity | Real-time performance shortfalls | 1 | 1 | 1 | Use common best practices | Loading time >1s | n/a | Jannik |  | 2025-04-12
9 | Project Comple-xity | High level of technical complexity | 2 | 2 | 4 | n/a | No one under-stands the code-base anymore | Refactor code | Leon |  | 2025-04-16